Coastline Auto Detailing — Glen Mills, PA

Second location business plan · Target launch: March 2028 · Prepared September 2026

© 2026 Morgan / Coastline Auto Detailing. All rights reserved. Confidential — do not copy or share without written permission.

# 1. Overview

Coastline Auto Detailing will open a second mobile detailing location serving Glen Mills, PA (19342) and the surrounding Delaware County and Chester County area, including Media, Chadds Ford and West Chester. It will run the same way as Athens, GA: Morgan runs the business; local technicians and subcontractors do the work; leads come from Google Local Services Ads first, then Meta ads for ceramic coating and high-ticket jobs.

# 2. Services and pricing

Starting point is the Athens price list. Set final PA prices in September 2027 after checking local competitors.

| Service | Athens price | Tech pay | Lead fee | Kept |
| --- | --- | --- | --- | --- |
| Full detail | $250 | $85 | $25 | $140 |
| Interior detail | $200 | $70 | $25 | $105 |
| Exterior wash | $170 | $40 | $25 | $105 |
| Ceramic coating / paint correction | TBD | ~30–35% | — | TBD |

# 3. Timeline

| When | What |
| --- | --- |
| Sep 2027 | Business setup: entity decision with an accountant; PA foreign registration ($250 filing fee, if using the Georgia LLC) with a PA registered agent; insurance covering PA; tax and licensing check; PA price list. |
| Oct–Nov 2027 | Marketing setup: Google Business Profile (Glen Mills service area), local number in GoHighLevel, Glen Mills website page, booking and follow-up automations. |
| Dec 2027–Jan 2028 | Team: hire 2 technicians and sign 1–2 subcontractors; paid test details before hiring. |
| Feb 2028 | Launch prep: training, equipment, Google Local Services Ads approval in PA, soft-launch customers, subcontractor agreements. |
| Mar 2028 | Launch. |

# 4. Team

## Technicians

- Local benchmark (Sep 2026): dealership detailers in Glen Mills earn about $15–20/hour (CarShop Glen Mills $15–17; Concordville Nissan $18–20).

- Coastline pays per job. At Athens rates, 3 full details a day is $255/day, which beats dealership pay.

- Recruit through Indeed, ZipRecruiter, local dealerships and car washes on Baltimore Pike, community college auto programs, and referrals from Athens techs.

- Offer per-job pay, paid training and a path to lead tech. Always run a paid test detail.

## Subcontractor candidates (researched Sep 2026)

| Business | Area | Contact |
| --- | --- | --- |
| Spearko's Mobile Auto Detailing | Glen Mills; Delaware + Chester County | +1 570-350-1773 |
| Attention To Detail Mobile Detailing | Glen Mills; PA, NJ, DE; fleet work | (833) 533-8245 |
| RideRevived LLC | Glen Mills, Chadds Ford; paint correction | riderevived.com |
| On-Site Detailing | Chadds Ford, West Chester | onsitedetailing.net |
| Blackline Auto Detailing | West Chester / Chester County | autodetailingofchestercounty.com |

Every subcontractor agreement must cover: per-job price, the Coastline quality checklist, customer ownership (customers belong to Coastline), no soliciting Coastline customers, and a certificate of insurance.

# 5. Marketing

- Google Local Services Ads from day one; answer every lead within 5 minutes.

- 1–2 Google reviews a day from the first week.

- Daily Instagram posts with local before/afters.

- Meta ceramic coating ads once there are local before/afters.

# 6. Launch budget (to be filled with real quotes)

| Item | Estimate |
| --- | --- |
| PA foreign registration filing fee | $250 (PA Dept. of State, 2026) |
| PA registered agent (per year) | Get quote |
| Commercial liability insurance | Get quote |
| Equipment and supplies for PA techs | Estimate |
| Google Local Services Ads (first month) | Budget |
| Website page, profile, printing | Estimate |
| Paid test details | Estimate |
| Buffer | Estimate |

Job postings, businesses and fees change. Re-check everything at each milestone. Jarvis sends reminders on Sep 1 2027, Dec 1 2027, Feb 1 2028 and Mar 1 2028.