## Timeline
Coastline #2 — Glen Mills, PA launch (March 2028)
Yellow cells are yours to update. Status options: Not started, In progress, Done.
Phase | When | What to do | Status | Notes
1. Business setup | Sep 2027 | Decide entity with an accountant; if using the Georgia LLC, file PA foreign registration ($250) with a PA registered agent; get insurance covering PA; check PA tax/licensing; set PA prices. | Not started
2. Marketing setup | Oct–Nov 2027 | Google Business Profile with Glen Mills service area; local number in GoHighLevel; Glen Mills page on website; booking + instant follow-up automations; start PA content. | Not started
3. Team | Dec 2027–Jan 2028 | Post tech jobs, contact subcontractors, interview, run paid test details. Goal: 2 techs + 1–2 subcontractors signed. | Not started
4. Launch prep | Feb 2028 | Train techs on checklist/quality; equipment and supplies; apply for Google Local Services Ads in PA; line up soft-launch customers; sign subcontractor agreements. | Not started
5. Launch | Mar 2028 | Turn on Google ads; answer leads within 5 minutes; 1–2 Google reviews a day; daily Instagram before/afters; add Meta ceramic ads once local before/afters exist; track PA revenue separately. | Not started

## Setup Checklist
Setup checklist
Mark each item Done as you finish it. Progress updates automatically.
# | Task | Due | Status | Notes
1 | Business entity decision (same LLC or new) with an accountant | Sep 2027 | Not started
2 | PA foreign registration filed ($250 filing fee) if using the Georgia LLC | Sep 2027 | Not started
3 | PA registered agent | Sep 2027 | Not started
4 | Commercial liability insurance covering PA | Sep 2027 | Not started
5 | PA tax registration and local rules checked with an accountant | Sep 2027 | Not started
6 | PA price list set | Sep 2027 | Not started
7 | Google Business Profile (Glen Mills service area) verified | Nov 2027 | Not started
8 | Local phone number + booking flow in GoHighLevel | Nov 2027 | Not started
9 | Glen Mills page on the website | Nov 2027 | Not started
10 | 2 techs hired | Jan 2028 | Not started
11 | 1–2 subcontractor agreements signed (with certificate of insurance) | Jan 2028 | Not started
12 | Techs trained on the Coastline checklist | Feb 2028 | Not started
13 | Equipment and supplies for PA techs | Feb 2028 | Not started
14 | Google Local Services Ads approved in PA | Feb 2028 | Not started
15 | Soft-launch customers lined up | Feb 2028 | Not started
16 | Jarvis: PA techs added, PA revenue tracked separately | Mar 2028 | Not started
Done
Progress

## Tech Recruiting
Tech recruiting
Local pay benchmarks (as of Sep 2026 — re-check in Dec 2027), then track candidates below. Row 13 is an example; replace it.
Local benchmark | Pay | Details | Source
CarShop Glen Mills — Automotive Detailer | $15–17/hr | 1021 Baltimore Pike; full-time, benefits | https://www.ziprecruiter.com/c/CarShop/Job/Automotive-Detailer/-in-Glen-Mills,PA?jid=b9e788d490ee5df1
Concordville Nissan — Detailer | $18–20/hr | Glen Mills; full-time | https://www.indeed.com/q-car-detailing-l-glen-mills,-pa-jobs.html
Indeed — car detailing jobs, Glen Mills | ~85 postings | Where to post your job and find candidates | https://www.indeed.com/q-car-detailing-l-glen-mills,-pa-jobs.html
Indeed — detailer jobs, Delaware County | ~66 postings | Wider area | https://www.indeed.com/q-detailer-l-delaware-county,-pa-jobs.html
Glassdoor — Glen Mills car detailing |  | More postings and pay data | https://www.glassdoor.com/Job/glen-mills-car-detailing-jobs-SRCH_IL.0,10_IC1152593_KO11,24.htm
Your per-job pay (from Athens rates): full $85, interior $70, exterior $40 — 3 full details a day = $255/day, above dealership hourly pay.
Candidate | Phone / email | Where found | Experience | Test detail date | Test result | Status | Notes
Example: Jordan S. | (610) 555-0100 | Indeed | 2 yrs dealership detailer | 2028-01-10 | Good — fast, clean interiors | Offer sent | Available weekends

## Subcontractors
Subcontractor candidates
Local detailers found Sep 2026. They're also competitors — pitch them as overflow partners. Re-check before contacting.
Business | Area | Phone | Link | Status | Per-job price agreed | COI received? | Notes
Spearko's Mobile Auto Detailing | Glen Mills; Delaware + Chester County | +1 570-350-1773 | https://www.yelp.com/biz/spearkos-mobile-auto-detailing-glen-mills | Not contacted
Attention To Detail Mobile Detailing | Glen Mills; PA, NJ, DE; fleet work | (833) 533-8245 | https://www.attentiontodetail4pa.com/ | Not contacted
RideRevived LLC | Glen Mills, Chadds Ford; paint correction |  | https://riderevived.com/glen-mills | Not contacted
On-Site Detailing | Chadds Ford, West Chester, Delaware County |  | https://www.onsitedetailing.net/chadds-ford.html | Not contacted
Blackline Auto Detailing | West Chester / Chester County |  | https://autodetailingofchestercounty.com/ | Not contacted
National Detail Pros directory | Glen Mills area detailers | (800) 601-0626 | https://nationaldetailpros.com/pennsylvania/glen-mills | Not contacted
Subcontractor agreement must cover:
• Per-job price
• Your quality checklist
• The customer belongs to Coastline
• No soliciting your customers
• Their certificate of insurance (COI)

## Launch Budget
Launch budget
Blue/yellow = your estimates. Only the PA filing fee is a known number; fill in the rest with real quotes.
Item | Estimated cost ($) | Source / note
PA foreign registration filing fee | 250 | PA Department of State (fee as of 2026); only if using the Georgia LLC
PA registered agent (per year) |  | Get a quote
Commercial liability insurance (first year) |  | Get a quote
Equipment and supplies for PA techs |  | Your estimate
Google Local Services Ads (first month) |  | Your budget
Website page, business profile, printing |  | Your estimate
Paid test details for tech candidates |  | Your estimate
Buffer (unexpected costs) |  | Your estimate
Total
Note on B5: Source: PA Department of State, Foreign Registration Statement fee as of 2026 (per Nolo / PA DOS). Re-check before filing.

## Sources
Sources
Researched September 2026. Businesses, job posts and fees change — re-check at each milestone.
Topic | Link
BBB: mobile detailing near Glen Mills | https://www.bbb.org/us/pa/glen-mills/category/mobile-auto-detailing
Spearko's (Roadtrippers) | https://maps.roadtrippers.com/us/glen-mills-pa/services/spearkos-mobile-auto-detailing
Attention To Detail (Yelp) | https://www.yelp.com/biz/attention-to-detail-mobile-detailing-glen-mills
Yelp: auto detailing near Media, PA | https://www.yelp.com/search?cflt=auto_detailing&find_loc=Media,+PA+19063
Yelp: auto detailing in West Chester, PA | https://www.yelp.com/search?cflt=auto_detailing&find_loc=West+Chester%2C+PA
Yelp: auto detailing in Chadds Ford, PA | https://www.yelp.com/search?cflt=auto_detailing&find_loc=Chadds+Ford,+PA
Berardi's Detailing (West Chester) | https://berardisdetailing.com/
PA Department of State: foreign associations | https://www.pa.gov/agencies/dos/programs/business/types-of-filings-and-registrations/foreign-associations
Nolo: registering a foreign LLC in PA | https://www.nolo.com/legal-encyclopedia/how-qualify-foreign-business-pennsylvania.html